## 1. Pre-Cutover Items
Item Number | Item | Applied Env | Task Owner | Action By | Duration (Minute) | Start Time | End Time | Release Notes/Action plan | Remarks
6 | Update DB configuration of each center/N4T/N4B server | [7 empty] | [TBC]
7 | Update Tomcat user on all N4T nodes | All | SSM | App Admin | 15 |  |  |  | Use tomcat-users.xml directly in “/app/navis/configuration/cluster/conf” or make new one as SOP mentioned
15 | Update ECN4 setting | All | SSM | App Admin | 5 |  |  | Add below setting in "equipment" component of D:\Navis\Data\ecn4\conf\ecn4_setting_prod.xml <setting name="ALLOW_TWIN_HAZARD_DISPATCH" value="true"/>
21 | Data marsking for N4B | Non-PROD | SSM | App Admin | 10 |  |  |  | This is only applied to non-production environment

## 2. Cutover Items
Item Number | Item | Applied Env | Task Owner | Action By | Duration (Minutes) | Start Time | End Time | TBC | Need Re-retrieve release resources | Release note | Remark
2 | Extract N4T/N4B background job and scheduled job list as an Excel | All | SSM | App Admin | 5 |  |  | Y | Y |  | Including scheduled EDI/SNX/Groovy/default/reporting jobs
6 | backup XPS data folder | All | SSM | App Admin | 5 |  |  |  | Y | Backup below folder from XPS server for both DCBI and DCBD D:\Navis\Data\xps\data D:\Navis\Data\xps\database D:\Navis\Data\xps\settings.xml
7 | Execute DB update script | All | SSM | DBA | 30
13 | Remove MTL Topology in operator | All | SSM | App Admin | 2 |  |  | Y |  | Choose "Complex MTLHK" and delete | [TBC] Need further confirm this release order
16 | Add DCBD in center node | All | SSM | App Admin | 5
29 | Update N4T Password settings by UI | All | SSM | App Admin | 2 |  |  |  | Y | Update the value of N4T Password settings if it is unmatched with the corresponding item in the attached Excel
31 | Update sparcs settings for DCBI and DCBD both | All | SSM | App Admin | 5 |  |  |  |  | Copy and replace the files to XPS server folder: D:\Navis\Data\XPS\Data folder
32 | Start DCBI bridge and XPS services | All | SSM | App Admin | 10
33 | Start DCBD bridge and XPS services | All | SSM | App Admin | 10
37 | Update N4T database backed variform | All | SSM | App Admin | 30 |  |  |  | Y | Refer to "Variforms" tab
38 | Update unit fields for gross weight | All | SSM | App Admin | 5
39 | Update event types by data patch | All | SSM | App Admin | 5 |  |  |  | Y
40 | Update custom menus | All | SSM | App Admin | 120 |  |  |  |  | Refer to "Custom Menus" tab | [On Demand] If the custom menu does not exit in each complex leve, then update custom menus
47 | Update N4T IReport Designs in Yard Level | All | DCB IT | App Admin | 5 |  |  | Y | Y | Import SNX | 请按顺序导入，因为存在后面覆盖前面部分的情况 1. [Yard level: DCBI] IReport_DCBI.snx 2. [Yard level: DCBD] IReport_DCBD.snx - 3. [Yard level: DCBI] STA0140_Barge_Operation_Design_DCBI.snx 4. [Yard level: DCBI] STA0180 CARGO INSPECTION DATA__DCBI__Designs (2).SNX 5. [Yard level: DCBI] DCBI_ALLFIELD-UNIT_Designs.SNX 6. [Yard level: DCBD] DCBD_DALLFIELD-UNIT_Designs.SNX
54 | Update N4T job groups | All | SSM | App Admin | 20 |  |  |  | Y |  | Startup all N4 3.8 cluster nodes and verify them all active via cluster service
55 | Update N4B job groups | All | SSM | App Admin | 10 |  |  |  | Y
67 | Update XPS server IP | PROD |  | IO Team |  |  |  | Y |  |  | [TBC] This is applied only to production
68 | Double check QCVMT DB link | All |  | DBA | 5 |  |  |  |  | Need to link to N4O DB
69 | Create DB Schema in N4O, and update for QCVMT | All |  | DBA | 32 |  |  |  |  | Perform all items of "DBA Action" tab
71 | Update N4T roles in operator level | All | SSM | App Admin | 2 |  |  |  | Y | Import SNX
74 | check the account "casapi" and it's password | All | DCB IT | App Admin | 2 |  |  |  |  | The account "casapi" and it's password in the tomcate-user.xml of tomcat should be same with the account in N4.
78 | Update N4T Integration Service | Non-PROD | SSM | App Admin | 3 |  |  |  |  | Update the URL of "CAS-Outbound" in tab "Integration Service": update navisusr.frm_integration_service set intserv_url = 'refer to below URL' where intserv_name = 'CAS-Outbound'; URL: SIT : http://10.24.254.7:6060/argo/services/ArgobasicServicePort UAT : http://10.24.254.7:7070/argo/services/ArgobasicServicePort
79 | Update General Reference | Non-PROD | DCB IT | App Admin | 5 |  |  | Y |  | Refer to "General Reference" UAT: update navisusr.argo_general_reference set value1 = 'http://172.25.12.123/MSA/ServiceReceive.asmx?wsdl' where ref_type = 'MSA_SOAP_ADDRESS' and cpx_gkey = (select gkey from argo_complex where ID = 'DCBI'); | [TBC] Lack configuration for SIM env, and if need sync update for DCBD in N4T and N4B both
79 | Update General Reference | Non-PROD | DCB IT | App Admin | 5 |  |  | Y |  | Refer to "General Reference" UAT: update navisusr.argo_general_reference set value1 = 'http://172.25.12.123/MSA/ServiceReceive.asmx?wsdl' where ref_type = 'MSA_SOAP_ADDRESS' and cpx_gkey = (select gkey from argo_complex where ID = 'DCBI'); | [TBC] Lack configuration for SIM env, and if need sync update for DCBD in N4T and N4B both

## 3. Variforms
Required variform list (total: 23, extract by SIT at 10:00, 2020-08-07)
Enabled | Level | Scope | Action | Name | Description | XML Template | Created | Changed | Variform IDs
TRUE | Operator | MTL | Update | CUSTOM_FORM_UNIT_DAMAGED_ICON | CUSTOM_FORM_UNIT_DAMAGED_ICON |  | 16-Sep-20 2248 | 20-May-04 1523 | ¦FORM_UNIT_ICON¦
TRUE | Operator | MTL | Update | CUSTOM_INV019_New | V3.8 Customized_INV019_Units_Physical_Status |  | 16-Sep-20 2227 | 20-Aug-04 1942 | ¦INV019¦
TRUE | Operator | MTL | Update | CUSTOM_INV049 | CUSTOM_INV049 |  | 16-Sep-20 2253 | 20-Jul-23 1155 | ¦INV049¦
TRUE | Operator | MTL | Update | CUSTOM_INV066 | Customization of INV066 |  | 17-Nov-01 1640 | 20-May-04 1521 | ¦INV066¦
TRUE | Operator | MTL | Create | CUSTOM_MYLIST_NEW | V3.8 Customization Table Units My List | TABLE | 20-May-04 1519 | 20-Jul-13 2002 | ¦TABLE_MYLIST¦
TRUE | Operator | MTL | Create | CUSTOM_N4_MOBILE_JOB_LIST_NEW | V3.8 Customization of MHCJOBLIST | TABLE | 20-Jun-17 0903 | 20-Jun-17 1039 | ¦MHCJobList¦
TRUE | Operator | MTL | Create | CUSTOM_PREADVISEDUINTS_NEW | V3.8 Customization of Table Preadvised Units | TABLE | 20-Jun-28 2155 | 20-Jun-28 2233 | ¦INV_TABLE_PREADVISED_UNITS¦
TRUE | Complex | MTL/DCBD | Create | CUSTOM_ROAD_MOBILE_FORM_DCBD_NEW | V3.8 Customization of road mobile forms in DCBD | FORM | 20-Aug-06 2220 | 20-Aug-06 2220 | ¦MROD001¦MROD002¦MROD002Buttons¦MRODUnitFlexFields¦MROD003¦MROD004¦MROD005¦MROD006¦MROD007¦MROD009¦MROD010¦MROD011¦MROD012¦MROD019¦MROD013¦MROD014¦MROD015¦MROD016¦MROD017¦MROD020¦MROD021¦MROD022¦BUNDLED_EQUIPMENT_DAMAGES_FORM¦MROD023¦MROD024¦MROD025¦MROD026¦MROD027¦MROD028¦BUNDLE_EQUIP_CUSTOM_DAMAGES_FORM¦MROD029¦MROD030¦MROD031¦MROD032¦MROD033¦MROD034¦
TRUE | Complex | MTL/DCBI | Create | CUSTOM_ROAD_MOBILE_FORM_DCBI_NEW | V3.8 Customization of road mobile forms in DCBI | FORM | 20-Aug-06 2221 | 20-Aug-06 2222 | ¦MROD001¦MROD002¦MROD002Buttons¦MRODUnitFlexFields¦MROD003¦MROD004¦MROD005¦MROD006¦MROD007¦MROD009¦MROD010¦MROD011¦MROD012¦MROD019¦MROD013¦MROD014¦MROD015¦MROD016¦MROD017¦MROD020¦MROD021¦MROD022¦BUNDLED_EQUIPMENT_DAMAGES_FORM¦MROD023¦MROD024¦MROD025¦MROD026¦MROD027¦MROD028¦BUNDLE_EQUIP_CUSTOM_DAMAGES_FORM¦MROD029¦MROD030¦MROD031¦MROD032¦MROD033¦MROD034¦
FALSE | Operator | MTL | Update | CUSTOM_ROAD_MOBILE_FORM_Disabled | V3.8 Customization of road mobile forms |  | 13-Oct-02 1805 | 20-Aug-06 2209 | ¦MROD001¦MROD002¦MROD002Buttons¦MRODUnitFlexFields¦MROD003¦MROD004¦MROD005¦MROD006¦MROD007¦MROD009¦MROD010¦MROD011¦MROD012¦MROD019¦MROD013¦MROD014¦MROD015¦MROD016¦MROD017¦MROD020¦MROD021¦MROD022¦BUNDLED_EQUIPMENT_DAMAGES_FORM¦MROD023¦MROD024¦MROD025¦MROD026¦MROD027¦MROD028¦BUNDLE_EQUIP_CUSTOM_DAMAGES_FORM¦MROD029¦MROD030¦MROD031¦MROD032¦MROD033¦MROD034¦
TRUE | Operator | MTL | Update | CUSTOM_ROD061_NEW | V3.8 CUSTOM_ROD061 for setting up E EIR |  | 17-Aug-17 0916 | 20-Jul-29 1701 | ¦ROD061¦
FALSE | Operator | MTL | Create | CUSTOM_TABLE_ POINT_OF_WORK | V3.8 Customization of Table POW | TABLE | 20-Jul-31 0055 | 20-Jul-31 0125 | ¦TABLE_POINTS_OF_WORK¦
TRUE | Operator | MTL | Update | CUSTOM_VESSEL_MOBILE_FORM_NEW | V3.8 Customization of vessel mobile forms |  | 13-Oct-02 1804 | 20-Jun-16 1316 | ¦MHC001¦MHC002¦MHC003¦MHC004¦MHC005¦MHC006¦MHC007¦MHC012¦MHC013¦MHC014¦MHC015¦MHC016¦MHC017¦MHC018¦MHC019¦MHC020¦MHC021¦MHC022¦MHC023¦MHC024¦MHC025¦MHC026¦MHC027¦MHC028¦MHC029¦MHC030¦MHC031¦MNHCModeSelection¦MNHCVesselCrane¦MNHCContainer¦MNHCIndividualCntrs¦MNHCLoad¦MNHCLoad1¦MNHCLoad2¦MNHCLoad3¦MNHCLoad4¦MNHCLoad1FlexFields¦MNHCLoad2FlexFields¦MNHCLoad3FlexFields¦MNHCLoad4FlexFields¦MNHCDschStatus¦MNHCDuplicateButtons¦MNHCWtInsp¦MNHCPlacardInsp¦MNHCBundleInsp¦MNHCSealsInsp¦MNHCDamageInsp¦MNHCNewDamageInsp¦MNHCBundleDamageInsp¦MNHCBndlDamageCodeInsp¦MNHCCreateOrphan¦MNHCShift¦MNHCOutOfGauge¦MNHCDispatch¦MNHCCraneActivityTracking¦MNHCFlexFields¦MNHCDirectReceiveDeliver¦MNHCContainerInspection¦
TRUE | Operator | MTL | Update | CUSTOM_VSL005_NEW | V3.8 Customization of VSL005 for FDR 103941and add berthing number |  | 13-Oct-02 1807 | 20-Jun-09 2247 | ¦VSL005¦
TRUE | Operator | MTL | Update | CUSTOM_VSL027 | Customization of VSL027 |  | 17-Nov-01 1640 | 20-May-29 1107 | ¦VSL027¦
TRUE | Operator | MTL | Update | CarrierVisitServiceOrderTable_NEW | V3.8 Customization of ORD072 - Custom CarrierVisitServiceOrderTable |  | 13-Oct-02 1804 | 20-Aug-05 0106 | ¦ORD072¦
TRUE | Operator | MTL | Update | Customization of Vessel Visit Inspector_Status | Customization of Vessel Visit Inspector_Status |  | 16-Sep-20 2245 | 20-Jul-16 1205 | ¦VESSEL_VISIT_STATUS¦
TRUE | Operator | MTL | Update | MTLRecordAttributeChangeDocument | New Form - MTLRecordAttributeChangeDocument |  | 13-Oct-02 1802 | 20-Jul-13 1358 | ¦MTLRecordAttributeChangeDocument¦
TRUE | Operator | MTL | Update | RoutingFormSubmissionCommand_New | V3.8 Customization of INV016 - RoutingFormSubmissionCommand (INV016) |  | 13-Oct-02 1802 | 20-Jun-17 1924 | ¦INV016¦
TRUE | Operator | MTL | Update | ServiceOrderTable_New | V3.8 Customization of ORD055 (Service Order) |  | 13-Oct-02 1751 | 20-Jun-08 2309 | ¦ORD055¦
TRUE | Operator | MTL | Update | UnitRecordServiceEvent_SRV022_NEW | V3.8 Customization of SRV022 (Record Service Event) |  | 13-Oct-02 1749 | 20-Jun-03 1932 | ¦SRV022¦
TRUE | Operator | MTL | Update | UnitsForm_New | V3.8 Customization of INV007 (Units Queries) |  | 13-Oct-02 1750 | 20-Aug-07 0238 | ¦INV007¦
TRUE | Operator | MTL | Update | Yard Inspection MYI002 | Yard Inspection MYI002 |  | 20-Jun-04 1656 |  | ¦MYI002¦
1. Update below variforms contents by pasting, and propagate change to all nodes.
- Retrieve from GitHub: https://github.com/DaChanBay/System-Source-Code/tree/master/N4T/Variform
2. Open tab "Database Backed Variforms", create new variform "CUSTOM_MYLIST". Edit contents by pasting, and propagate change to all nodes.

## 4. Custom Menus
Pre-checking: login N4T complex level for DCBI and DCBD separately, check that if exist below custom menus. If not, please perform below steps.
| DCBI (total: 21) |  | DCBD (total: 20)
1. Login N4 with facility level and open "custom menu items" tab
2. Select all custom menu items and click [-] to delete all of them
3. Recreate all custom menu as below. Need to login different complex to add for DCBI and DCBD separately
Active | Label | Id | Description | Variform | Preceding Menu | Position | Menu Tree | Destination | Level | Scope
TRUE | Acr TABLE | CUSTOM_NODE_ACR | CUSTOM_NODE_ACR | CUSTOM_TABLE_CUSTOMBPBILLREQUEST | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Acr TABLE | CUSTOM_NODE_ACR_DCBD | CUSTOM_NODE_ACR_DCBD | CUSTOM_TABLE_CUSTOMBPBILLREQUEST | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Active Tariff | CUSTOM_NODE_BP_ACTIVE_TARIFF | Active Tariff | CUSTOM_BP_ACTIVE_TARIFF_TABLE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Active Tariff | CUSTOM_NODE_BP_ACTIVE_TARIFF_DCBD | Active Tariff | CUSTOM_BP_ACTIVE_TARIFF_TABLE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | BP Attribute Event | CUSTOM_NODE_BPATTRIBUTEEVENT | CUSTOM_NODE_BPATTRIBUTEEVENT | CUSTOM_TABLE_CUSTOMBPATTRIBUTEEVENT | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | BP Attribute Event | CUSTOM_NODE_BPATTRIBUTEEVENT_DCBD | CUSTOM_NODE_BPATTRIBUTEEVENT_DCBD | CUSTOM_TABLE_CUSTOMBPATTRIBUTEEVENT | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | BP IAOC Rate | CUSTOM_NODE_BPIAOCSARATE_DCBD | CUSTOM_NODE_BPIAOCSARATE_DCBD | CUSTOM_TABLE_CUSTOMBPIAOCSARATE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | BP IAOC Rate | CUSTOM_NODE_BPIAOCSARATE | CUSTOM_NODE_BPIAOCSARATE | CUSTOM_TABLE_CUSTOMBPIAOCSARATE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | BP Late Charge | CUSTOM_NODE_BPLATECHARGE | CUSTOM_NODE_BPLATECHARGE | CUSTOM_TABLE_CUSTOMBPLATECHARGE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | BP Late Charge | CUSTOM_NODE_BPLATECHARGE_DCBD | CUSTOM_NODE_BPLATECHARGE_DCBD | CUSTOM_TABLE_CUSTOMBPLATECHARGE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | BP Physical Movement | CUSTOM_NODE_PHYSICALMOVEMENT | CUSTOM_NODE_PHYSICALMOVEMENT | CUSTOM_TABLE_CUSTOMBPPHYSICALMOVEMENT | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | BP Physical Movement | CUSTOM_NODE_PHYSICALMOVEMENT_DCBD | CUSTOM_NODE_PHYSICALMOVEMENT_DCBD | CUSTOM_TABLE_CUSTOMBPPHYSICALMOVEMENT | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Base Category | CUSTOM_NODE_BASE_CATEGORY_DCBD | CUSTOM_NODE_BASE_CATEGORY_DCBD | CUSTOM_TABLE_CUSTOMBPBASECATEGORY | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Base Category | CUSTOM_NODE_BASE_CATEGORY | CUSTOM_NODE_BASE_CATEGORY | CUSTOM_TABLE_CUSTOMBPBASECATEGORY | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Base Status | CUSTOM_NODE_BASE_STATUS_DCBD | Base Status | CUSTOM_TABLE_CUSTOMBPBASESTATUS | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Base Status | CUSTOM_NODE_BASE_STATUS | Base Status | CUSTOM_TABLE_CUSTOMBPBASESTATUS | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Billing | CUSTOM_NODE_BILLING | CUSTOM_NODE_BILLING |  | MID_REPORTS | Directly after chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Billing | CUSTOM_NODE_BILLING_DCBD | CUSTOM_NODE_BILLING_DCBD |  | MID_REPORTS | Directly after chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | CNY Calendar | CUSTOM_NODE_CNY_DCBD | CUSTOM_NODE_CNY_DCBD | CUSTOM_TABLE_CUSTOMBPCNYPERIOD | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | CNY Calendar | CUSTOM_NODE_CNY | CUSTOM_NODE_CNY | CUSTOM_TABLE_CUSTOMBPCNYPERIOD | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Cashier Indicator Setting | CUSTOM_NODE_CASHIER_INDICATOR | Cashier Indicator Setting | CUSTOM_TABLE_CUSTOMBPCASHIERINDICATOR | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Consolidate Invoice | CUSTOM_NODE_CON_INVOICE | Consolidate Invoice | CUSTOM_TABLE_CUSTOMBPCONSOINV | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Consolidate Invoice | CUSTOM_NODE_CON_INVOICE_DCBD | Consolidate Invoice | CUSTOM_TABLE_CUSTOMBPCONSOINV | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Custom Filter | CUSTOM_NODE_CUSTOM_FILTER | CUSTOM_NODE_CUSTOM_FILTER | CUSTOM_TABLE_CUSTOMBPCUSTOMERFILTER | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Custom Filter | CUSTOM_NODE_CUSTOM_FILTER_DCBD | CUSTOM_NODE_CUSTOM_FILTER_DCBD | CUSTOM_TABLE_CUSTOMBPCUSTOMERFILTER | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Customer Group | CUSTOM_NODE_CUSTOMER_GROUP | CUSTOM_NODE_CUSTOMER_GROUP | CUSTOM_TABLE_CUSTOMER_GROUP | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Customer Group | CUSTOM_NODE_CUSTOMER_GROUP_DCBD | CUSTOM_NODE_CUSTOMER_GROUP_DCBD | CUSTOM_TABLE_CUSTOMER_GROUP | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Empty Pool | CUSTOM_NODE_EMPTY_POOL_DCBD | EMPTY POOL | CUSTOM_EMPTYPOOL_TABLE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Empty Pool | CUSTOM_NODE_EMPTY_POOL | EMPTY POOL | CUSTOM_EMPTYPOOL_TABLE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Empty Pool Entitlement | CUSTOM_NODE_EMPTY_ENTITLEMENT | Empty Pool Entitlement | CUSTOM_EMPTY_ENTITLEMENT_TABLE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Empty Pool Entitlement | CUSTOM_NODE_EMTPY_ENTILEMENT_DCBD | Empty Pool Entitlement | CUSTOM_EMPTY_ENTITLEMENT_TABLE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | FSP Form | CUSTOM_NODE_FSP_FORM | FSP Form | CUSTOM_TABLE_CUSTOMBPFSPFORM | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | FSP Form | CUSTOM_NODE_FSP_FORM_DCBD | FSP Form | CUSTOM_TABLE_CUSTOMBPFSPFORM | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Invoice List | CUSTOM_NODE_INVOICE_LIST_DCBD | Invoice List | CUSTOM_TABLE_CUSTOMBPINVOICELIST | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Invoice List | CUSTOM_NODE_INVOICE_LIST | Invoice List | CUSTOM_TABLE_CUSTOMBPINVOICELIST | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Laden Pool | CUSTOM_NODE_LADEN_POOL | LADEN POOL | CUSTOM_LADENPOOL_TABLE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Laden Pool | CUSTOM_NODE_LADEN_POOL_DCBD | LADEN POOL | CUSTOM_LADENPOOL_TABLE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Report with Extraction | CUSTOM_NODE_REPORT_W_EXT | Report with Extraction | TABLE_REPORT_W_EXTRACTION | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Report with Extraction | CUSTOM_NODE_REPORT_W_EXT_DCBD | Report with Extraction | TABLE_REPORT_W_EXTRACTION | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | Request Table | CUSTOM_NODE_REQUEST_TABLE | Request Table | CUSTOM_TABLE_CUSTOMREQUESTTABLE | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI
TRUE | Request Table | CUSTOM_NODE_REQUEST_TABLE_DCBD | Request Table | CUSTOM_TABLE_CUSTOMREQUESTTABLE | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | VIP Form | CUSTOM_NODE_VIP_DCBD | VIP Form | CUSTOM_TABLE_BP_VIP_FORM | CUSTOM_NODE_BILLING_DCBD | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBD
TRUE | VIP Form | CUSTOM_NODE_VIP | VIP Form | CUSTOM_TABLE_BP_VIP_FORM | CUSTOM_NODE_BILLING | As first child of chosen menu | ApexNavigationTree_cpx.xml |  | Complex | MTL/DCBI

## 5. General Reference
Env | Item 1 | Type | ID-1 | ID-2 | ID-3 | Value-1 | Value-2 | Value-3 | Value-4 | Value-5 | Value-6
SIT DCBI | MSADATASOURCE | config | config |  |  | N4O DB IP | N4O DB Port | N4O DB SERVER | N4O DB SERVICE_NAME | N4O DB Account | N4O DB password
| MSA_CODE | config | config | test |  | WF-0135-0001 | DV-0135-000001
| MSA_MANIFEST | config | config |  |  | AU-0001 | 管理员 | AU-0001 | 管理员 | Poc#1001
| MSA_SOAP_ADDRESS | config | config |  |  | http://172.25.12.125/MSA/ServiceReceive.asmx?wsdl
UAT DCBI | MSADATASOURCE | config | config |  |  | N4O DB IP | N4O DB Port | N4O DB SERVER | N4O DB SERVICE_NAME | N4O DB Account | N4O DB password
| MSA_CODE | config | config | test |  | WF-0135-0001 | DV-0135-000001
| MSA_MANIFEST | config | config |  |  | AU-0001 | 管理员 | AU-0001 | 管理员 | Poc#1001
| MSA_SOAP_ADDRESS | config | config |  |  | http://172.25.12.123/MSA/ServiceReceive.asmx?wsdl
PROD DCBI | MSADATASOURCE | config |  |  |  | N4O DB IP(使用具体的DB的IP) | N4O DB Port（使用具体的DB的端口号）

## 6. DBA Action
Item Number | Item | Action By | Release note Or Action Plan | Remarks | Duration
1 | Create DCBLink Schema in N4O | DBA | Create dcblink/dcblinkapp schema reference these two schemas in ODS (include tables/views/synonyms) For DBLink: In SIT / UAT : DBLink of GOS link to GOSUAT ; Other link to GOS(PROD). | N4O DB | 10min
2 | SouthEport View reCreate | DBA |  | QCVMT DB | 5min
3 | BargeLink View reCreate | DBA |  | QCVMT DB | 2min
4 | BargeLink DB DBLink Update | DBA | In SIT/UAT/GOLDEN : DBLink in DBGU link to current Env QCMVT; In PROD : DBLink in DBGP link to QCVMT(PROD) |  | 5min
5 | Update the point of XPS_CHE table under the account jreportapp of QCVMT | DBA | In N4 2.6 ,the XPS_CHE of jreportapp of QCVMT is point to another account's view, but the ultimate point is N4's XPS_CHE table ; In N4 3.8 ,when without ODS, So need change the point to XPS_CHE of N4O. | QCVMT DB | 5min
6 | Update the point of EP_Barge_Schedule_vw view under the account epdata of QCVMT | DBA | In SIT/UAT/GOLDEN : EP_Barge_Schedule_vw Link to DBGU(BargeLink UAT DB); In PROD : EP_Barge_Schedule_vw Link to DBGP(BargeLink PROD DB) | QCVMT DB | 5min
7 | Data Patch : update the N4O table crg_bills_of_lading, set the created field to not null where the created is null | DBA | In SIT/UAT/GOLDEN/PROD : execute the sql attached | N4O DB

## 7. New Groovy Job
1. Create below DCBI/DCBD groovy job in N4T
1.1, Login N4T as DCBI/DCBD facility level separately
1.2, Open Groovy Job Sheet
1.3, Click [+] Button
1.4, fill in with below information to new groovy jobs
| Id | Description | Job Execution Group | Groovy Job User | Execution Scope Level | Execution Scope | Groovy Job Type | Included | Frequency | Execution Hour(s) | Execution Minute(s) | Email Message Subject | Success Recipient Email | Success Message Prefix | Error Recipient Email | Error Message Prefix
| DCBSYNCHBINS | DCBSynchBins | Depends on Environment | n4.dcbi.backgroundjob | Yard | MTL/DCBI/DCB1I/DCB1I | Groovy PlugIn | DCBSYNCHBINS | On Demand |  |  | DCBSynchBins in DCBI is executed | man.he@dcbTerminals.com | DCBSynchBins in DCBI is executed | man.he@dcbTerminals.com | DCBSynchBins in DCBI is failure
| DCBSYNCHBINS_DCBD | DCBSYNCHBINS_DCBD | Depends on Environment | n4.dcbd.backgroundjob | Yard | MTL/DCBD/DCB1D/DCB1D | Groovy PlugIn | DCBSYNCHBINS_D | On Demand |  |  | DCBSynchBins in DCBD is executed | man.he@dcbTerminals.com | DCBSynchBins in DCBD is executed | man.he@dcbTerminals.com | DCBSynchBins in DCBD is executed
| DCBIPURGEOBSWI |  | Depends on Environment | n4.dcbi.backgroundjob | Yard | MTL/DCBI/DCB1I/DCB1I | Groovy PlugIn | DCBPurgeObsWI | By Day of Week(Friday) | 12 | 19
| DCBDPURGEOBSWI |  | Depends on Environment | n4.dcbd.backgroundjob | Yard | MTL/DCBD/DCB1D/DCB1D | Groovy PlugIn | DCBPurgeObsWI | By Day of Week(Friday) | 12 | 19